## Issue Tracker
# | TASK | TYPE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
1 | domain and hosting | Type 2 | Medium | 2024-02-01 | Ramzan | 2024-02-04 | Ramzan | Done
2 | architecture design | Type 2 | Medium | 2024-02-01 | Ramzan | 2024-02-01 | Ramzan | Done
3 | requirment understanding | Type 3 | Medium | 2024-02-04 | Ramzan | 2024-02-01 | Ramzan | Done
4 | database design | Type 1 | Medium | 2024-02-04 | Ramzan | 2024-02-05 | Ramzan
5 | api design / development | Type 1 | Medium | 2024-02-04 | Ramzan | 2024-02-04 | Ramzan
6 | landing page design / development | Type 1 | Low | 2024-02-08 | Ramzan | 2024-02-08 | Ramzan
7 | books page design / development | Type 1 | High | 2024-02-08 | Ramzan | 2024-02-13 | Ramzan
8 | ai - quran page design / development | Type 2 | Medium | 2024-02-08 | Ramzan | 2024-02-11 | Ramzan
9 | media page design / development | Type 3 | Medium | 2024-02-08 | Ramzan | 2024-02-11 | Ramzan
10 | activity page design / development | Type 4 | High | 2024-02-12 | Ramzan | 2024-02-12 | Ramzan
11 | contact page design / development | Type 2 | Medium | 2024-02-12 | Ramzan | 2024-02-13 | Ramzan
12 | registration page design / development | Type 1 | High | 2024-02-15 | Ramzan | 2024-02-18 | Ramzan
13 | login page design / development | Type 2 | High | 2024-02-20 | Ramzan | 2024-02-20 | Ramzan
14 | profile page design / development | Type 2 | High | 2024-02-23 | Ramzan | 2024-02-23 | Ramzan
15 | mobile app - PWA | Type 2 | Low | 2024-02-26 | James | 2024-02-27 | Ramzan
16 | LOGO Design | Type 4 | Medium | 2024-02-26 | Lilly | 2024-02-26 | Iftikhar / suhail
17 | Biograhpy data | Type 2 | Low | 2024-02-26 | Ted | 2024-02-26 | Sahabaz
18 | all books file read / write / copy format | Type 3 | High | 2024-02-27 | Lilly | 2024-02-27 | Iftikhar / suhail
19 | islamic images event basis ( like eid-e-milad | Type 2 | Low | 2024-02-27 | Ted | 2024-02-27 | Iftikhar / suhail
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91

## calculations (hidden)
*** This sheet should remain hidden ***
|  |  | Min | 2023-01-01
Max
|  |  | Days | #REF!
|  |  | Date | #REF! | 1
|  |  | Type | #REF!
|  |  | Priority | #REF!
[5 empty] | #VALUE! | #VALUE!
[5 empty] | 5 | 4 | Sorted | Sorted
|  | Date | Opened | Closed | Types | Priorities | Types | Priorities
[5 empty] | * | *
| 1 | #REF! | 0 | 0 | Type 2 | Medium | * | *
| 2 | #REF! | 0 | 0 | Type 3 | Low | * | *
| 3 | #REF! | 0 | 0 | Type 1 | High | Type 1 | High
| 4 | #REF! | 0 | 0 | Type 4 | 0 | Type 2 | Low
| 5 | #REF! | 0 | 0 | 0 | #N/A | Type 3 | Medium
| 6 | #REF! | 0 | 0 | #N/A | #N/A | Type 4 | #NUM!
| 7 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 8 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 9 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 10 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 11 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 12 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 13 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 14 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 15 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 16 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 17 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 18 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 19 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 20 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 21 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 22 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 23 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 24 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 25 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 26 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 27 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 28 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 29 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 30 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 31 | #REF! | 0 | 0
| 32 | #REF! | 0 | 0
| 33 | #REF! | 0 | 0
| 34 | #REF! | 0 | 0
| 35 | #REF! | 0 | 0
| 36 | #REF! | 0 | 0
| 37 | #REF! | 0 | 0
| 38 | #REF! | 0 | 0
| 39 | #REF! | 0 | 0
| 40 | #REF! | 0 | 0
| 41 | #REF! | 0 | 0
| 42 | #REF! | 0 | 0
| 43 | #REF! | 0 | 0
| 44 | #REF! | 0 | 0
| 45 | #REF! | 0 | 0
| 46 | #REF! | 0 | 0
| 47 | #REF! | 0 | 0
| 48 | #REF! | 0 | 0
| 49 | #REF! | 0 | 0
| 50 | #REF! | 0 | 0
| 51 | #REF! | 0 | 0
| 52 | #REF! | 0 | 0
| 53 | #REF! | 0 | 0
| 54 | #REF! | 0 | 0
| 55 | #REF! | 0 | 0
| 56 | #REF! | 0 | 0
| 57 | #REF! | 0 | 0
| 58 | #REF! | 0 | 0
| 59 | #REF! | 0 | 0
| 60 | #REF! | 0 | 0
| 61 | #REF! | 0 | 0
| 62 | #REF! | 0 | 0
| 63 | #REF! | 0 | 0
| 64 | #REF! | 0 | 0
| 65 | #REF! | 0 | 0