## Issue Tracker
# | TASK | TYPE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
1 | domain and hosting | Type 2 | High | 2024-11-11 | Ramzan |  | Ramzan | Done
2 | architecture design | Type 2 | High | 2024-11-12 | Ramzan |  | Ramzan | Done
3 | requirment understanding | Type 2 | High | 2024-11-13 | Ramzan |  | Ramzan | Done
4 | database design | Type 2 | High | 2024-11-14 | Ramzan |  | Ramzan | Done
5 | api design / development | Type 2 | High | 2024-11-15 | Ramzan |  | Ramzan | Done
6 | Home Page Design / Development | Type 2 | High | 2024-11-16 | Ramzan |  | Ramzan | need to improve mobile based menu
7 | Books Page Design / Development | Type 2 | High | 2024-11-17 | Ramzan |  | Ramzan
8 | AI Quran Page Design / Development | Type 2 | High | 2024-11-18 | Ramzan |  | Ramzan
9 | Media Page Design / Development | Type 2 | High | 2024-11-19 | Ramzan |  | Ramzan
10 | Activity Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan |  | Ramzan | Done
11 | Contact Us Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan |  | Ramzan | Done
12 | About Us Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan |  | Ramzan | Done
13 | FeedBack Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan |  | Ramzan
14 | Donation Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan |  | Ramzan
15 | Biography Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan |  | Ramzan
16 | mobile app - PWA | Type 2 | Medium | 2024-11-23 | Ramzan
17 | multiple support language | Type 2 | Medium | 2024-11-23 | Ramzan
18 | GTM manager for website marketing | Type 2 | Medium | 2024-11-23 | Ramzan
19 | implements accessbilty | Type 2 | Medium | 2024-11-23 | Ramzan
20 | code review | Type 2 | Medium | 2024-11-23 | Ramzan
21 | code optimzation / security / UAT test | Type 2 | Medium | 2024-11-23 | Ramzan
22 | admin panel | Type 2 | Medium | 2024-11-23 | Ramzan
23 | LOGO Design | Type 2 | Medium | 2024-11-23 | Ifthikar
24 | all books file read / write / copy format | Type 2 | Medium | 2024-11-23 | Ramzan
25 | islamic images event basis ( like eid-e-milad | Type 2 | Medium | 2024-11-23 | Ifthikar
26 | Light mode / Dark mode | Type 2 | Medium | 2024-11-23 | Ramzan
28 | websites marketing | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## books data
# | Books Name | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## quran data
# | Quran Data | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## images data
# | Images Data | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## biograhapy data
# | Biography Details | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## media data
# | Media URL | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## activity data
# | Activity Data | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## contact us
# | Contact Us Details | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## about us
# | About Us Details | TYPE | PRIORITY | OPENED ON | OPENED BY
1 |  | Type 2 | High | 2024-11-11 | Ramzan
2 |  | Type 2 | High | 2024-11-12 | Ramzan
3 |  | Type 2 | High | 2024-11-13 | Ramzan
4 |  | Type 2 | High | 2024-11-14 | Ramzan
5 |  | Type 2 | High | 2024-11-15 | Ramzan
6 |  | Type 2 | High | 2024-11-16 | Ramzan
7 |  | Type 2 | High | 2024-11-17 | Ramzan
8 |  | Type 2 | High | 2024-11-18 | Ramzan
9 |  | Type 2 | High | 2024-11-19 | Ramzan
10 |  | Type 2 | Medium | 2025-03-15 | Ramzan
11 |  | Type 2 | Medium | 2025-03-15 | Ramzan
12 |  | Type 2 | Medium | 2025-03-15 | Ramzan
13 |  | Type 2 | Medium | 2025-03-15 | Ramzan
14 |  | Type 2 | Medium | 2025-03-15 | Ramzan
15 |  | Type 2 | Medium | 2025-03-15 | Ramzan
16 |  | Type 2 | Medium | 2024-11-23 | Ramzan
17 |  | Type 2 | Medium | 2024-11-23 | Ramzan
18 |  | Type 2 | Medium | 2024-11-23 | Ramzan
19 |  | Type 2 | Medium | 2024-11-23 | Ramzan
20 |  | Type 2 | Medium | 2024-11-23 | Ramzan
21 |  | Type 2 | Medium | 2024-11-23 | Ramzan
22 |  | Type 2 | Medium | 2024-11-23 | Ramzan
23 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
24 |  | Type 2 | Medium | 2024-11-23 | Ramzan
25 |  | Type 2 | Medium | 2024-11-23 | Ifthikar
26 |  | Type 2 | Medium | 2024-11-23 | Ramzan
28 |  | Type 2 | Medium | 2025-03-15 | Ramzan
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## calculations (hidden)
*** This sheet should remain hidden ***
|  |  | Min | 2024-01-01
Max
|  |  | Days | #REF!
|  |  | Date | #REF! | 1
|  |  | Type | #REF!
|  |  | Priority | #REF!
[5 empty] | #VALUE! | #VALUE!
[5 empty] | 2 | 3 | Sorted | Sorted
|  | Date | Opened | Closed | Types | Priorities | Types | Priorities
[5 empty] | * | *
| 1 | #REF! | 0 | 0 | Type 2 | High | * | *
| 2 | #REF! | 0 | 0 | 0 | Medium | * | *
| 3 | #REF! | 0 | 0 | #N/A | 0 | Type 2 | High
| 4 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | Medium
| 5 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 6 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 7 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 8 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 9 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 10 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 11 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 12 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 13 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 14 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 15 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 16 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 17 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 18 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 19 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 20 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 21 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 22 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 23 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 24 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 25 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 26 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 27 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 28 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 29 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 30 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 31 | #REF! | 0 | 0
| 32 | #REF! | 0 | 0
| 33 | #REF! | 0 | 0
| 34 | #REF! | 0 | 0
| 35 | #REF! | 0 | 0
| 36 | #REF! | 0 | 0
| 37 | #REF! | 0 | 0
| 38 | #REF! | 0 | 0
| 39 | #REF! | 0 | 0
| 40 | #REF! | 0 | 0
| 41 | #REF! | 0 | 0
| 42 | #REF! | 0 | 0
| 43 | #REF! | 0 | 0
| 44 | #REF! | 0 | 0
| 45 | #REF! | 0 | 0
| 46 | #REF! | 0 | 0
| 47 | #REF! | 0 | 0
| 48 | #REF! | 0 | 0
| 49 | #REF! | 0 | 0
| 50 | #REF! | 0 | 0
| 51 | #REF! | 0 | 0
| 52 | #REF! | 0 | 0
| 53 | #REF! | 0 | 0
| 54 | #REF! | 0 | 0
| 55 | #REF! | 0 | 0
| 56 | #REF! | 0 | 0
| 57 | #REF! | 0 | 0
| 58 | #REF! | 0 | 0
| 59 | #REF! | 0 | 0
| 60 | #REF! | 0 | 0
| 61 | #REF! | 0 | 0
| 62 | #REF! | 0 | 0
| 63 | #REF! | 0 | 0
| 64 | #REF! | 0 | 0
| 65 | #REF! | 0 | 0