## Issue Tracker
# | TASK | TYPE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
1 | domain and hosting | Type 2 | High | 2024-11-11 | Ramzan | Done | Ramzan
2 | architecture design | Type 2 | High | 2024-11-12 | Ramzan | Done | Ramzan
3 | requirment understanding | Type 2 | High | 2024-11-13 | Ramzan | Done | Ramzan
4 | database design | Type 2 | High | 2024-11-14 | Ramzan
5 | api design / development | Type 2 | High | 2024-11-15 | Ramzan
6 | Home Page Design / Development | Type 2 | High | 2024-11-16 | Ramzan | Done | Ramzan
7 | Books Page Design / Development | Type 2 | High | 2024-11-17 | Ramzan | Done | Ramzan
8 | AI Quran Page Design / Development | Type 2 | High | 2024-11-18 | Ramzan | Done | Ramzan
9 | Media Page Design / Development | Type 2 | High | 2024-11-19 | Ramzan | Done | Ramzan
10 | Activity Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan | Done | Ramzan
11 | Contact Us Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan | Done | Ramzan
12 | About Us Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan | Done | Ramzan
13 | FeedBack Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan | Done | Ramzan
14 | Donation Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan | Done | Ramzan
15 | Biography Page Design / Development | Type 2 | Medium | 2025-03-15 | Ramzan | InProgress | Ramzan
16 | mobile app - PWA ( https://www.crocs.in/ ) | Type 2 | Medium | 2024-11-23 | Ramzan | done | Ramzan
17 | multiple support language | Type 2 | Medium | 2024-11-23 | Ramzan | Done | Ramzan
18 | GTM manager for website marketing | Type 2 | Medium | 2024-11-23 | Ramzan
19 | implements accessbilty | Type 2 | Medium | 2024-11-23 | Ramzan
20 | code review | Type 2 | Medium | 2024-11-23 | Ramzan | InProgress | Ramzan
21 | code optimzation / security / UAT test | Type 2 | Medium | 2024-11-23 | Ramzan | InProgress | Ramzan
22 | admin panel | Type 2 | Medium | 2024-11-23 | Ramzan | InProgress | Ramzan
23 | LOGO Design | Type 2 | Medium | 2024-11-23 | Ifthikar | InProgress | Ramzan
24 | all books file read / write / copy format | Type 2 | Medium | 2024-11-23 | Ramzan | Done | Ramzan
25 | islamic images event basis ( like eid-e-milad | Type 2 | Medium | 2024-11-23 | Ifthikar | InProgress | Ramzan
26 | Light / Dark features ( https://web.dev/ ) | Type 2 | Medium | 2024-11-23 | Ramzan
28 | websites marketing | Type 2 | Medium | 2025-03-15 | Ramzan
29 | UI / UX Design based page | Type 2 | Medium | 2025-03-15 | Ramzan
30 | convert css file into scss for better code readabilty | Type 2 | Medium | 2025-03-15 | Ramzan
31 | website scrolling issues / Fit all content in same page without scrolling | Bug | Medium | 2025-03-15 | Ramzan
32 | Finalize website color , bgcolor and font-family and font-size across the web site for all lang like urdu hindi arbic and english | Bug | Medium | 2025-03-15 | Ramzan
33 | Biography content writing | Type 2 | Medium | 2024-11-23 | Shabaz
34 | Book data Collection | Type 2 | Medium | 2024-11-23 | Ifthikar | InProgress
35 | AI Quran Data Collection | Type 2 | Medium | 2024-11-23 | Ifthikar / Product Owner | InProgress
36 | Media Data Collection ( Links Youtube ) | Type 2 | Medium | 2024-11-23 | Ifthikar / Product Owner | InProgress
37 | Donation Data Collection ( Bank Data ) | Type 2 | Medium | 2024-11-23 | Product Owner | InProgress
38 | Activities Data and websites images Collection ( Lanagar khana etc ) | Type 2 | Medium | 2024-11-23 | Product Owner | InProgress
39 | Local DB setup. create json database and angular sevices for all components | Type 2 | Medium | 2024-11-23 | Ramzan | InProgress
40 | In repo create folder abulfatah and paste all books into this
41 | follow the naming convention
42
43 | Kanjul Iman | Quran | Pakisatan | Best | ok ok normal
44 | books Books page | Add read books from website
45 | book mobile view | show 2books in same row | done
46 | HomePage - on click carusol image click | onclick of of images open it or zoom it | done
47 | Book mobile view - remove category part and implement as discuused approch oly | remove catroy part and design as per old approach | done
48 | media page isssue |  | done
49
50
51
52
53
54
55
56
84
85
86
87
88
89
90
91

## MEDIA
Sr. No | Title | Category | Writer | Recitor | Link
1 | Faaslon ko taqalluf hai humse agar | Naat |  | Qari Waheed Zafar | https://youtu.be/GZkbK1NXuas?si=OmuTbMDXgrzSfdRE
2 | Huzoor Aisa Koi Intezam Hojaye | Naat |  | Syed Fasihuddin Soharwardi | https://youtu.be/yIOo1gRbb-U?si=bAYXK1moHW8VZA8w
3 | Maula Ya Salli Wa sallim- Qaseeda Burda Shareef | Naat |  | Mahmood ul hassan Ashrafi | https://youtu.be/y4LerDDGoNM?si=SlabsW4g1LkljAnM
4 | Sabse Aula wa Aala hamara Nabi | Naat | Aalahazrat | Mahmood ul hassan Ashrafi | https://youtu.be/ntOvZoTFTRY?si=KDSaN2IrARoFjjQG
5 | Koi Duniya e Ata mai nahi Hamta Tera | Naat | Aalahazrat | Syed Hassan Ullah Hussaini | https://youtu.be/i8YyekWrbhU?si=fXzHpxMwWIukZUJJ
6 | Dar Bada ho to sawali bhi khada sajta hai | Naat |  | Syed Hassan Ullah Hussaini | https://youtu.be/-SZajol3vpI?si=NAmIcpqv3Iod4CJ7
7 | Koi Duniya e Ata mai nahi Hamta Tera | Naat | Aalahazrat |  | https://youtu.be/ipaKE4bcQ4Y?si=irUJZgpf09M9uXpY
8 | Lutf Unka aam Ho hi jayega | Naat | Aalahazrat | Allama Farooq ul hasan | https://youtu.be/bzFPkYc6AzM?si=fOWY2jsKC3SoxoMY
9 | Koi Gul baqi rahega na Chaman Reh jayega | Naat | Syed Kafi Miyan | Allama Farooq ul hasan | https://youtu.be/imgpBLb6g0E?si=KhQ2VRRMIjX3oX-I
10 | Subho taiba mai huwi Batta Hai baada Noor ka | Naat | Aalahazrat | Allama Farooq ul hasan | https://youtu.be/FwP6SfqdVlM?si=1_HF7x8lBJRnLzIU
11 | Tere Qadmo mai aana mera kaam tha | Naat |  | Muhammad Hassan Raza Qadri | https://youtu.be/BaPTR0SSXZo?si=krBvP7wDsuMUjGdt
12 | Shere Sunnat Hain | Manqabat |  | Mahmood Raza/ Hassan Raza | https://youtu.be/kSOpCVJ-uxM?si=l9xDa5LD-FyQ1tzh
13 | Shere Beshae Ahlesunnat Maulana Hashmat Ali | Manqabat |  | Hafiz Bilal Qadri | https://youtu.be/OPu8PjYYW7Y?si=HiIKCqaUDRm5wu9W
14 | Hashmati Rang mai rang jao mere yaar | Manqabat | Allama Faraan Raza | Rao Brothers | https://youtu.be/A8sS_qxCWJg?si=7vzaUNSG9-aln0Df
15 | Mazhare Aalahazrat Chale aaiye | Manqabat | Sarkar Mashood e Millat | Hafiz Bilal Qadri | https://youtu.be/nnFJwA6vwQg?si=EpgW-sNln-SldjnM
16 | Shere Sunnat rehnuma Hashmat Ali Khan Qadri | Manqabat |  | Hafiz Mazhar Ashrafi | https://youtu.be/w-jpQaMBWmM?si=qg5fV9dvvDEqBsb-
17 | Jo tujhe bhool gaya mazhare Aalahazrat | Manqabat |  | Shakeel Aarfi | https://youtu.be/mbP0rKor95A?si=X9AzFreEMAm7sek2
18 | Nadroon ko ilm ke moti Aaqa ne Ata kiye | Naat |  | Hassan Nizami | https://youtu.be/Bly17hO2O6A?si=0Dd0pcefjeDYcdKM
19 | Muhammad Hamare Badi shaan wale (Sallallahu Alaihi wasallam) | Naat |  | Hassan Nizami | https://youtu.be/XHvFELfqFkw?si=wH2LHfhM31VyuOsV
20 | Aankho ka tara Naame Muhammad (Sallallahu Alaihi wasallam) | Naat |  | Allama Manahil Raza Hashmati | https://youtu.be/jIWQnFVPDLA?si=b1jqCgXNx_Tz54d5
21 | Waah kya ilm Hai hazrate Aala Tera | Manqabat | Sarkar Mazhar e Aalahazrat | Allama Manahil Raza Hashmati | https://youtu.be/B5ouofBAsJc?si=IS8Nk5JgqvnYd9UN
22 | Chalo Dekhlen wo haqeeqaten jinhe dekhna bhi misaal hai | Naat | Allama Faraan Raza | Allama Manahil Raza Hashmati | https://youtu.be/aTcRF2gHf-Q?si=i45LjW8WUqQ48bkA
23 | Tere Jalwo Ki tabani Moinuddin Ajmeri | Manqabat | Sarkar Mashood e Millat | Allama Manahil Raza Hashmati | https://youtu.be/BiR4R6t1Tm4?si=GVlt1jPa9Nu9w8oo
24 | Hazaro mai 72 Tan the tasleem o raza wale | Manqabat |  | Allama Manahil Raza Hashmati | https://youtu.be/t2GPjYft0q4?si=l_kv_q9ntyuVfiRl
25 | Baghe jannat ke hain behre madhkhwane Ahlebait | Manqabat | Sarkar Ustade Zaman | Allama Manahil Raza Hashmati | https://youtu.be/EDyA9Op51uo?si=x1wdPQ52SHVVMet-
26 | Peshe Haq Muzda Shafa'at ka sunate jayenge | Naat | Sarkar Aalahazrat | Allama Manahil Raza Hashmati | https://youtu.be/cBmWTjcxWBk?si=rhXkJVt8u3qFEtE6
27 | Karte hain jinno bashar har waqt charcha Ghous ka | Manqabat |  | Allama Manahil Raza Hashmati | https://youtu.be/3vCZ6Zz8D00?si=knjYd_Nr4omwiFrL
28 | Zameeno zaman tumhare liye | Naat | Sarkar Aalahazrat | Allama Manahil Raza Hashmati | https://youtu.be/CVSJeZf9MG8?si=9eljinBRkKTlm52W
29 | Zeenate Yaseen Tui | Naat | Sarkar Jami | Allama Manahil Raza Hashmati | https://youtu.be/Pz3MR8Wqblw?si=l51C-Y2QmOb1oHem

## BIOGRAPHY
BIO

## calculations (hidden)
*** This sheet should remain hidden ***
|  |  | Min | 2024-01-01
Max
|  |  | Days | #REF!
|  |  | Date | #REF! | 1
|  |  | Type | #REF!
|  |  | Priority | #REF!
[5 empty] | #VALUE! | #VALUE!
[5 empty] | 8 | 5 | Sorted | Sorted
|  | Date | Opened | Closed | Types | Priorities | Types | Priorities
[5 empty] | * | *
| 1 | #REF! | 0 | 0 | Type 2 | High | * | *
| 2 | #REF! | 0 | 0 | Bug | Medium | * | *
| 3 | #REF! | 0 | 0 | 0 | 0 | Add read books from website | done
| 4 | #REF! | 0 | 0 | Quran | Pakisatan | Bug | High
| 5 | #REF! | 0 | 0 | Add read books from website | done | onclick of of images open it or zoom it | Medium
| 6 | #REF! | 0 | 0 | show 2books in same row | #N/A | Quran | Pakisatan
| 7 | #REF! | 0 | 0 | onclick of of images open it or zoom it | #N/A | remove catroy part and design as per old approach | #NUM!
| 8 | #REF! | 0 | 0 | remove catroy part and design as per old approach | #N/A | show 2books in same row | #NUM!
| 9 | #REF! | 0 | 0 | #N/A | #N/A | Type 2 | #NUM!
| 10 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 11 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 12 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 13 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 14 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 15 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 16 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 17 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 18 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 19 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 20 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 21 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 22 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 23 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 24 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 25 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 26 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 27 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 28 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 29 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 30 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 31 | #REF! | 0 | 0
| 32 | #REF! | 0 | 0
| 33 | #REF! | 0 | 0
| 34 | #REF! | 0 | 0
| 35 | #REF! | 0 | 0
| 36 | #REF! | 0 | 0
| 37 | #REF! | 0 | 0
| 38 | #REF! | 0 | 0
| 39 | #REF! | 0 | 0
| 40 | #REF! | 0 | 0
| 41 | #REF! | 0 | 0
| 42 | #REF! | 0 | 0
| 43 | #REF! | 0 | 0
| 44 | #REF! | 0 | 0
| 45 | #REF! | 0 | 0
| 46 | #REF! | 0 | 0
| 47 | #REF! | 0 | 0
| 48 | #REF! | 0 | 0
| 49 | #REF! | 0 | 0
| 50 | #REF! | 0 | 0
| 51 | #REF! | 0 | 0
| 52 | #REF! | 0 | 0
| 53 | #REF! | 0 | 0
| 54 | #REF! | 0 | 0
| 55 | #REF! | 0 | 0
| 56 | #REF! | 0 | 0
| 57 | #REF! | 0 | 0
| 58 | #REF! | 0 | 0
| 59 | #REF! | 0 | 0
| 60 | #REF! | 0 | 0
| 61 | #REF! | 0 | 0
| 62 | #REF! | 0 | 0
| 63 | #REF! | 0 | 0
| 64 | #REF! | 0 | 0
| 65 | #REF! | 0 | 0