## Issue Tracker
# | TASK | TYPE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
1 | domain and hosting | Type 2 | High | 2024-11-11 | Ramzan |  | Ramzan | Done
2 | architecture design | Type 2 | High | 2024-11-12 | Ramzan |  | Ramzan | Done
3 | requirment understanding | Type 2 | High | 2024-11-13 | Ramzan |  | Ramzan | Done
4 | database design | Type 2 | High | 2024-11-14 | Ramzan |  | Ramzan | Done
5 | api design / development | Type 2 | High | 2024-11-15 | Ramzan |  | Ramzan | Done
6 | landing page design / development | Type 2 | High | 2024-11-16 | Ramzan |  | Ramzan | Done
7 | books page design / development | Type 2 | High | 2024-11-17 | Ramzan |  | Ramzan
8 | ai - quran page design / development | Type 2 | High | 2024-11-18 | Ramzan |  | Ramzan
9 | media page design / development | Type 2 | High | 2024-11-19 | Ramzan |  | Ramzan
10 | activity page design / development | Type 2 | Medium | 2024-11-20 | Ramzan |  | Ramzan | Done
11 | contact page design / development | Type 2 | Medium | 2024-11-21 | Ramzan |  | Ramzan | Done
13 | user management desing / development | Type 2 | Medium | 2024-11-23 | Ramzan |  | Ramzan | Done
14 | profile page design / development | Type 2 | Medium | 2024-11-24 | Ramzan |  | Ramzan | Done
15 | mobile app - PWA | Type 2 | Medium | 2024-11-25 | Ramzan |  | Ramzan | Done
16 | multiple support language | Type 2 | Medium | 2024-11-26 | Ramzan |  | Ramzan
17 | GTM manager for website marketing | Type 2 | Medium | 2024-11-27 | Ramzan |  | Ramzan
18 | implements accessbilty | Type 2 | Medium | 2024-11-28 | Ramzan |  | Ramzan
19 | code review | Type 2 | Medium | 2024-11-28 | Ramzan |  | Ramzan
20 | code optimzation / security / UAT test | Type 2 | Medium | 2024-11-28 | Ramzan |  | Ramzan
21 | admin panel | Type 2 | Medium | 2024-11-28 | Ramzan |  | Ramzan
22 | LOGO Design | Type 2 | Medium | 2024-11-28 | Iftikhar / suhail |  | Iftikhar / suhail
23 | Biograhpy data | Type 2 | High | 2024-11-28 | Sahabaz |  | Sahabaz
24 | all books file read / write / copy format | Type 2 | High | 2024-11-28 | Iftikhar / suhail |  | Iftikhar / suhail
25 | islamic images event basis ( like eid-e-milad | Type 2 | High | 2024-11-28 | Iftikhar / suhail |  | Iftikhar / suhail
26
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91

## calculations (hidden)
*** This sheet should remain hidden ***
|  |  | Min | 2023-01-01
Max
|  |  | Days | #REF!
|  |  | Date | #REF! | 1
|  |  | Type | #REF!
|  |  | Priority | #REF!
[5 empty] | #VALUE! | #VALUE!
[5 empty] | 2 | 3 | Sorted | Sorted
|  | Date | Opened | Closed | Types | Priorities | Types | Priorities
[5 empty] | * | *
| 1 | #REF! | 0 | 0 | Type 2 | High | * | *
| 2 | #REF! | 0 | 0 | 0 | Medium | * | *
| 3 | #REF! | 0 | 0 | #N/A | 0 | Type 2 | High
| 4 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | Medium
| 5 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 6 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 7 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 8 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 9 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 10 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 11 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 12 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 13 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 14 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 15 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 16 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 17 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 18 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 19 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 20 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 21 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 22 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 23 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 24 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 25 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 26 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 27 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 28 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 29 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 30 | #REF! | 0 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 31 | #REF! | 0 | 0
| 32 | #REF! | 0 | 0
| 33 | #REF! | 0 | 0
| 34 | #REF! | 0 | 0
| 35 | #REF! | 0 | 0
| 36 | #REF! | 0 | 0
| 37 | #REF! | 0 | 0
| 38 | #REF! | 0 | 0
| 39 | #REF! | 0 | 0
| 40 | #REF! | 0 | 0
| 41 | #REF! | 0 | 0
| 42 | #REF! | 0 | 0
| 43 | #REF! | 0 | 0
| 44 | #REF! | 0 | 0
| 45 | #REF! | 0 | 0
| 46 | #REF! | 0 | 0
| 47 | #REF! | 0 | 0
| 48 | #REF! | 0 | 0
| 49 | #REF! | 0 | 0
| 50 | #REF! | 0 | 0
| 51 | #REF! | 0 | 0
| 52 | #REF! | 0 | 0
| 53 | #REF! | 0 | 0
| 54 | #REF! | 0 | 0
| 55 | #REF! | 0 | 0
| 56 | #REF! | 0 | 0
| 57 | #REF! | 0 | 0
| 58 | #REF! | 0 | 0
| 59 | #REF! | 0 | 0
| 60 | #REF! | 0 | 0
| 61 | #REF! | 0 | 0
| 62 | #REF! | 0 | 0
| 63 | #REF! | 0 | 0
| 64 | #REF! | 0 | 0
| 65 | #REF! | 0 | 0